## Week 16
Sithcare Project Gantt Timeline
Activity | Start Week | Duration
Project Initiation | 1 | 1
Team Formation & Role Assignment | 1 | 1
GitHub Organization Setup | 1 | 1
Repository Configuration | 1 | 1
Sprint 1 – Project Setup & Planning | 1 | 2
Research Planning | 2 | 1
Literature Review | 2 | 2
Competitive Analysis | 2 | 2
Stakeholder Interviews | 2 | 2
Patient Questionnaire & Survey | 3 | 2
Sprint 2 – Requirements Engineering | 3 | 2
SRS Development | 3 | 3
Use Case Modelling | 3 | 2
Activity Diagrams | 4 | 2
Sprint 3 – System Design | 5 | 2
Architecture Design | 5 | 2
Database Design | 5 | 2
UI Wireframes (Figma) | 5 | 2
User Flow Design | 5 | 2
Dashboard Mockups | 6 | 2
SDS Development | 5 | 3
Sprint 4 – Platform Development | 8 | 5
Frontend Development | 8 | 5
Backend Development | 8 | 5
Database Implementation | 8 | 4
Authentication Module | 8 | 3
Appointment Module | 9 | 3
Telemedicine Module | 9 | 3
Community Module | 10 | 2
Emergency Module | 10 | 2
Notification Module | 10 | 2
Admin Dashboard | 10 | 3
Backend Integration | 11 | 2
Frontend Integration | 11 | 2
System Testing | 13 | 2
Bug Fixing | 14 | 1
Deployment | 15 | 1
Final Documentation | 15 | 1
Final Presentation | 16 | 1
Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Project Initiation | █
Team Formation | █
GitHub Setup | █
Repository Configuration | █
Sprint 1 | █ | █
Research |  | █ | █
Literature Review |  | █ | █
Competitive Analysis |  | █ | █
Stakeholder Interviews |  | █ | █
Patient Questionnaire |  |  | █ | █
Sprint 2 |  |  | █ | █
SRS Development |  |  | █ | █ | █
Use Cases |  |  | █ | █
Sprint 3 |  |  |  |  | █ | █
Architecture Design |  |  |  |  | █ | █
Database Design |  |  |  |  | █ | █
UI Wireframes |  |  |  |  | █ | █
SDS Development |  |  |  |  | █ | █ | █
Sprint 4 | [6 empty] | █ | █
Design Review | [6 empty] | █
Design Validation (Testing) | [6 empty] | █ | █
Bug Fixing | [7 empty] | █
Repository Finalisation (Deployment) | [7 empty] | █
Final Documentation | [7 empty] | █
Final Presentation | [7 empty] | █

## Week 8
Activity | Start Week | Duration
Project Initiation | 1 | 1
Team Formation & Role Assignment | 1 | 1
GitHub Organization Setup | 1 | 1
Repository Configuration | 1 | 1
Sprint 1 – Project Planning & Setup | 1 | 2
Research & Literature Review | 2 | 2
Competitive Analysis | 2 | 2
Stakeholder Interviews | 2 | 2
Patient Questionnaire | 3 | 2
Sprint 2 – Requirements Engineering | 3 | 2
SRS Development | 3 | 3
Use Case & Activity Diagrams | 3 | 2
Sprint 3 – System Design | 5 | 2
Architecture Design | 5 | 2
Database Design | 5 | 2
UI Wireframes & Prototype | 5 | 2
SDS Development | 5 | 3
Sprint 4 – Design Finalisation | 7 | 2
Design Review & Integration | 7 | 1
Design Validation (Testing) | 7 | 2
Bug Fixing / Review Feedback | 8 | 1
Repository Finalisation (Deployment) | 8 | 1
Final Documentation | 8 | 1
Final Presentation | 8 | 1
Sithcare Project - Gantt Chart
| Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
| Project Initiation | █
| Team Formation | █
| GitHub Setup | █
| Repository Configuration | █
| Sprint 1 | █ | █
| Research |  | █ | █
| Literature Review |  | █ | █
| Competitive Analysis |  | █ | █
| Stakeholder Interviews |  | █ | █
| Patient Questionnaire |  |  | █ | █
| Sprint 2 |  |  | █ | █
| SRS Development |  |  | █ | █ | █
| Use Cases |  |  | █ | █
| Sprint 3 |  |  |  |  | █ | █
| Architecture Design |  |  |  |  | █ | █
| Database Design |  |  |  |  | █ | █
| UI Wireframes |  |  |  |  | █ | █
| SDS Development |  |  |  |  | █ | █ | █
| Sprint 4 | [6 empty] | █ | █
| Design Review | [6 empty] | █
| Design Validation (Testing) | [6 empty] | █ | █
| Bug Fixing | [7 empty] | █
| Repository Finalisation (Deployment) | [7 empty] | █
| Final Documentation | [7 empty] | █
| Final Presentation | [7 empty] | █